## Project Overview
th
SYSTEM TEST CASE TEMPLATE Version 0.2
GENERAL INFORMATION
| Project Name | Bus Ticketing
| Project Code | BTM-0625
| Start Date | 2025-02-01
| End Date | 07/31/2025
KEY MEMBERS
| Project Manager | Nguyen Nhuan Tien
| Business Analyst | Nguyen Pham Hong Ngoc
| Project Technical Lead | Nguyen Le Thao Vi
| QC Lead | Nguyen Le Thao Vi

## Revision
DOCUMENT REVISION HISTORY
No. | Version No. | Creation Date | Description | Author | Reviewed By Date | Approved By Date | Remarks
1 | 0.1 | 01/02/2025 | Create test cases for bus ticketing system | Nguyen Nhuan Tien
2 | 0.2 | 07/31/2025 | Add more test cases for the system | Nguyen Le Thao Vi
3
4
5
CHECKLIST TEMPLATE REVISION HISTORY
No. | Version No. | Creation Date | Description | Author | Reviewed By Date | Approved By Date | Remarks
1 | 0.1 | 01/02/2025 | Create a checklist for system testing | Nguyen Nhuan Tien
2 | 0.2 | 07/31/2025 | Update the testing checklist | Nguyen Le Thao Vi
3
4
5

## Test Overall
SYSTEM TEST CASE OVERALL
No. | Sheet name | Latest Date of Test | Total Test case | Round 1 |  |  |  | Round 2 |  |  |  | Round 3 |  |  |  | Remarks
|  |  |  | Platform A |  | Platform B |  | Platform A |  | Platform B |  | Platform A |  | Platform B
|  |  |  | Passed | Failed | Passed | Failed | Passed | Failed | Passed | Failed | Passed | Failed | Passed | Failed
1 | LOGIN/REGISTER | 15/06/2025 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Tested: This function is related to function at current sprint (sprint 2)>
2 | Search Trip Screen | 2025-06-15 | 34 | 20 | 8 | 5 | 1
3 | Reserve Vehicle Screen | 2025-06-16 | 9 | 8 | 1
4 | Booking history screen | 2025-06-16 | 25 | 10 | 7 | 6 | 2
5 | Ticket information screen | 2025-06-17 | 12 | 6 | 2 | 4
6 | Ticket information screen | 2025-06-17 | 12 | 6 | 2 | 4
7
8
9
10
Total |  |  | 124 | 62 | 20 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## LOGINREGISTER
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Platform 1 | Platform 2 | Platform 1 | Platform 2 | Platform 1 | Platform 2
Nguyen Pham Hong Ngoc | 09/26/2017 |  | User Story 321 | ID-001~ID-0014 |  | PASSED | 12 | 0 | 0 | 0 | 0 | 0 | 12
[6 empty] | FAILED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 12 | 0 | 0 | 0 | 0 | 0 | 12
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID
ID-001 | Login | Valid Login | User has an existing account | Verify login with valid credentials | 1. Open login page 2. Enter valid email & password 3. Click Login | User is successfully logged in | Passed |  |  | 03/28/2025 | Nhuan Tien
ID-002 | Login | Valid Login | User has an existing account Facebook/Google | Verify login with valid credentials | 1. Open login page 2. ELogin with Facebook/Google 3. Click Login | User is successfully logged in | Passed |  |  | 03/28/2025 | Nhuan Tien
ID-003 | Login | Invalid Login | User entered wrong password | Verify login with incorrect password | 1. Open login page 2. Enter valid email & incorrect password 3. Click Login | Error message: "Invalid credentials" | Passed |  |  | 03/28/2025 | Thao Vi
ID-004 | Login | Invalid Login | Non-existent Account | Identify unregistered account login information | 1. Open login page 2. Enter user name/unregistered email & any password 3. Click Login | Error message: "User not found" | Passed |  |  | 03/28/2025 | Nhuan Tien
ID-005 | Login | Invalid Login | User has an existing account | Verify login with wrong password multiple times | 1. Open login page 2. Enter valid email & incorrect password 3. Click Login | Error message: "CAPTCHA" or temporarily lock account for 1 minute. | Passed |  |  | 03/28/2025 | Le Vi
ID-006 | Login | Empty Required Fields | N/A | Verify login with empty fields | 1. Open login page 2. Leave email & password blank 3. Click Login | Error message: "Fields cannot be empty" | Passed |  |  | 03/28/2025 | Le Vi
ID-007 | Register | Valid Register | N/A | Verify registration with valid details | 1. Open register page 2. Enter valid name, phone number, email, password 3. Click Register | User account is successfully created | Passed |  |  | 03/28/2025 | Nhuan Tien
ID-008 | Register | Valid Register | N/A | Verify registration with Facebook/Google account | 1. Open register page 2. Enter your Facebook/Google account) 3. Click Register | User account is successfully created | Passed |  |  | 03/28/2025 | Le Vi
ID-009 | Register | Duplicate Email | Email is already registered | Verify registration with an already registered email | 1. Open register page 2. Enter existing email & password 3. Click Register | Error message: "Email already in use" | Passed |  |  | 03/28/2025 | Nhuan Tien
ID-0010 | Register | Empty Fields | N/A | Verify registration with empty fields | 1. Open register page 2. Leave fields blank 3. Click Register | Error message: "Fields cannot be empty" | Passed |  |  | 03/28/2025 | Le Vi
ID-0011 | Register | Weak password | User enters weak password | Verify registered password | 1. Open register page 2. Enter password 3. Click Register | Error message: "Weak password, enter at least 6 characters" | Passed |  |  | 03/28/2025 | Le Vi
ID-0012 | Register | Password does not match | User confirms password does not match | Verify registered password | 1. Open register page 2. Enter password 3. Click Register | Error message: "Passwords do not match" | Passed |  |  | 03/28/2025 | Nhuan Tien
ID-0013
ID-0014
ID-0015
ID-0016
ID-0017
ID-0018
ID-0019
ID-0020
ID-0021
ID-0022
ID-0023
ID-0024

## Search Trip Screen
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Platform 1 | Platform 2 | Platform 1 | Platform 2 | Platform 1 | Platform 2
Nguyen Le Thao Vi | 03/26/2025 |  | User Story 321 | ID-001~ID-0014 |  | PASSED | 2 | 3 | 0 | 0 | 0 | 0 | 5
[6 empty] | FAILED | 3 | 0 | 0 | 0 | 0 | 0 | 3
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 5 | 5 | 5 | 5 | 5 | 5 | 30
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID
ID-001 | Open [Search] screen | UI Elements Display | App is installed and user is logged in | Verify that all UI elements are displayed correctly | 1. Open the app and navigate to the Search screen. 2. Observe if all elements (input fields, buttons, icons, etc.) are visible. | All elements (e.g., "From", "To", "Date", "Search button", navigation bar icons) should be displayed correctly. | Passed |  |  | 15/06/2025 | Nhuan Tien |  |  |  | 09/26/2017 |  |  |  |  | 09/26/2017
ID-002 | Open [Search] screen | Input Functionality | App is installed and user is logged in | Verify that the "From" input field works correctly | 1. Open the app and navigate to the Search screen. 2. Tap on the "From" input field. 3. Enter a location name (e.g., "Lien Chieu"). 4. Observe if the input is accepted correctly. | The input field should accept text input, display the entered text properly, and suggest relevant locations if applicable. | Failed | Passed |  | 15/06/2025 | Hong Ngoc
ID-003 | Open [Search] screen | Input Functionality | App is installed and user is logged in | Verify that the "To" input field works correctly | 1. Open the app and navigate to the Search screen. 2. Tap on the "To" input field. 3. Enter a location name (e.g., "Ngu Hanh Son"). 4. Observe if the input is accepted correctly. | The input field should accept text input, display the entered text properly, and suggest relevant locations if applicable. | Failed | Passed |  | 15/06/2025 | Nhuan Tien
ID-004 | Open [Search] screen | Date Picker Functionality | App is installed and user is logged in | Verify that the Date Picker works correctly | 1. Open the app and navigate to the Search screen. 2. Tap on the Date field. 3. Select a date from the date picker. 4. Observe if the selected date is displayed in the input field. | The selected date should be displayed correctly in the "Date" field in the correct format (DD/MM/YYYY). The date selected must be today or a future date, not a date in the past. | Failed | Passed |  | 15/06/2025 | Hong Ngoc
ID-005 | Open [Search] screen | Search Button Functionality | App is installed and user is logged in | Verify that the Search button functions correctly | 1. Open the app and navigate to the Search screen. 2. Enter valid values in "From", "To", and "Date" fields. 3. Tap the "Search" button. 4. Observe the search results. | The app should display a list of available buses for the selected route and date. The transition should be smooth with no lag. | Passed |  |  | 2025-06-15 | Nhuan Tien
ID-006
ID-007
ID-008
ID-009
ID-0010
ID-0011
ID-0012
ID-0013
ID-0014
ID-0015
ID-0016
ID-0017
ID-0018
ID-0019
ID-0020
ID-0021
ID-0022
ID-0023
ID-0024

## Reserve Vehicle Screen
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Platform 1 | Platform 2 | Platform 1 | Platform 2 | Platform 1 | Platform 2
Nguyen Le Thao Vi | 03/26/2025 |  | User Story 321 | ID-001~ID-0014 |  | PASSED | 3 | 3 | 0 | 0 | 0 | 0 | 6
[6 empty] | FAILED | 3 | 0 | 0 | 0 | 0 | 0 | 3
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 6 | 6 | 6 | 6 | 6 | 6 | 36
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID
ID-001 | Reserve Vehicle Screen | UI Elements Display | App is installed and user is on this screen | Verify that all UI elements are displayed correctly | 1. Open the app and navigate to the "Reserve Vehicle" screen. 2. Observe if all elements (input fields, labels, buttons) are visible. | All UI elements (e.g., "Preferred Date", "Full Name", "Email", "Contact") should be displayed correctly. | Passed |  |  | 16/06/2025 | Nhuan Tien
ID-002 | Reserve Vehicle Screen | Input Functionality | App is installed and user is on this screen | Verify that the "Preferred Date" input field works correctly | 1. Tap on the "Preferred Date" field. 2. Select a date from the calendar. 3. Observe if the selected date is displayed correctly. | The selected date should be displayed correctly in the input field in "DD/MM/YYYY" format. The date selected must be today or a future date, not a date in the past. | Failed | Passed |  | 16/06/2025 | Hong Ngoc
ID-003 | Reserve Vehicle Screen | Input Functionality | App is installed and user is on this screen | Verify that the "Full Name" input field works correctly | 1. Tap on the "Full Name" input field. 2. Enter a name (e.g., "John Doe"). 3. Observe if the input is accepted correctly. | The input field should accept text input and display the entered text properly. | Passed |  |  | 16/06/2025 | Nhuan Tien
ID-004 | Reserve Vehicle Screen | Input Functionality | App is installed and user is on this screen | Verify that the "Email" input field works correctly | . Tap on the "Email" input field. 2. Enter an email (e.g., "test@example.com"). 3. Observe if the input is accepted correctly. | The input field should accept valid email input and display the entered text properly. | Failed | Passed |  | 16/06/2025 | Hong Ngoc
ID-005 | Reserve Vehicle Screen | Input Functionality | App is installed and user is on this screen | Verify that the "Contact" input field works correctly | 1. Tap on the "Contact" input field. 2. Enter a phone number (e.g., "0123456789"). 3. Observe if the input is accepted correctly. | The input field should accept numeric input and display the entered text properly. | Passed |  |  | 2025-06-16 | Nhuan Tien
ID-006 | Reserve Vehicle Screen | Navigation Functionality | App is installed and user is on this screen | Verify that the back button functions correctly | 1. Tap on the back button ("←"). 2. Observe if the app navigates back to the previous screen. | The app should navigate back to the previous screen smoothly when the back button is tapped. | Failed | Passed |  | 2025-06-16 | Hong Ngoc
ID-007
ID-008
ID-009
ID-0010
ID-0011
ID-0012
ID-0013
ID-0014
ID-0015
ID-0016
ID-0017
ID-0018
ID-0019
ID-0020
ID-0021
ID-0022
ID-0023
ID-0024

## Booking history screen
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Platform 1 | Platform 2 | Platform 1 | Platform 2 | Platform 1 | Platform 2
Nguyen Nhuan Tien | 03/26/2025 |  | User Story 321 | ID-001~ID-0014 |  | PASSED | 5 | 0 | 0 | 0 | 0 | 0 | 5
[6 empty] | FAILED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 5 | 5 | 5 | 5 | 5 | 5 | 30
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID
ID-001 | Open [Booking List] screen | Booking List Display | App is installed, user is logged in, and user has at least one booking | Verify that the booking list displays correctly | 1. Open the "Bookings history" screen. 2. Check each ticket to ensure it displays the following details correctly: +Ticket image (VARBINARY) +Bus company name (TEXT) +Departure date and time (Date Time) | At step 2: - Each ticket should display a valid image, the correct bus company name, and the right departure date and time. | Passed |  |  | 16/6/2025
ID-002 | Open [Booking List] screen | Pay Button Functionality | App is installed, user is logged in, and user has at least one booking | Verify that the Pay button works correctly | 1. Open the "Bookings history" screen. 2. Click the "Pay" button on an unpaid ticket. | At step 2: - The app should navigate to the payment screen. | Passed |  |  | 16/6/2025
ID-003 | Open [Booking List] screen | Cancel Button Functionality | App is installed, user is logged in, and user has at least one booking | Verify that the Cancel button works correctly | 1. Open the "Bookings history" screen. 2. Click the "Cancel" button on an unpaid ticket. | At step 2: - A confirmation pop-up should appear, asking for confirmation to cancel the booking. | Passed |  |  | 16/6/2025
ID-004 | Open [Booking List] screen | Ticket Status Display | App is installed, user is logged in, and user has at least one booking | Verify that the ticket status displays correctly | 1. Open the "Bookings history" screen. 2. Check the status of each ticket. | At step 2: - If the ticket is paid, it should display "Paid." - If the ticket is canceled, it should display "Refund" with the message "The bus service has been cancelled." | Passed |  |  | 16/6/2025
ID-005 | Open [Booking List] screen | Back Button Functionality | App is installed, user is logged in, and user has at least one booking | Verify that the Back button works correctly | 1. Open the "Bookings history" screen. 2. Click the back button (top left corner). | At step 2: - The app should navigate back to the home screen. | Passed |  |  | 16/6/2025
ID-006
ID-007
ID-008
ID-009
ID-0010
ID-0011
ID-0012
ID-0013
ID-0014
ID-0015
ID-0016
ID-0017
ID-0018
ID-0019
ID-0020
ID-0021
ID-0022
ID-0023
ID-0024

## Ticket information screen
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Platform 1 | Platform 2 | Platform 1 | Platform 2 | Platform 1 | Platform 2
Nguyen Nhuan Tien | 03/26/2025 |  | User Story 321 | ID-001~ID-0014 |  | PASSED | 5 | 0 | 0 | 0 | 0 | 0 | 5
[6 empty] | FAILED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 5 | 5 | 5 | 5 | 5 | 5 | 30
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID |  |  | Platform A | Platform B | Bug ID
ID-001 | Open [Payment methods] screen | Payment methods List Display | App is installed, user is logged in, and user user must have at least one unpaid booking. | Verify that all payment methods are displayed correctly. | 1. Open the "Payment methods" screen. 2. Check if the following payment options are displayed: Banking (Payment by bank transfer) E-Wallet (Payment using e-wallet) Physically (Pay with cash) 3. Check each payment to ensure it displays the following details correctly: + Payment image (VARBINARY) + Payment name (TEXT) + Payment description (TEXT) | At step 2: - All three payment methods should be visible. At step 3: - All three payment methods should display a valid image, the correct payment name, and the right description. | Passed |  |  | 17/6/2025 | [9 empty] | 09/26/2017
ID-002 | Open [Payment methods] screen | Banking Button Functionality | App is installed, user is logged in, and user user must have at least one unpaid booking. | Verify that the Banking button works correctly | 1. Open the "Payment methods" screen. 2. Click on the "Banking" option. | At step 2: - The screen should display the banking details pop-up for payment. (e.g., QR code, account number, bank name,...) | Passed |  |  | 17/6/2025
ID-003 | Open [Payment methods] screen | E-wallet Button Functionality | App is installed, user is logged in, and user user must have at least one unpaid booking. | Verify that the E-wallet button works correctly | 1. Open the "Payment methods" screen. 2. Click on the "E-wallet" option. | At step 2: - The device should automatically open the default e-wallet app. - If multiple e-wallet apps are installed, the user should be prompted to choose an app. - If no e-wallet app is installed, the app should show an error message. | Passed |  |  | 17/6/2025
ID-004 | Open [Payment methods] screen | Cash Status Display | App is installed, user is logged in, and user user must have at least one unpaid booking. | Verify that the Cash button works correctly | 1. Open the "Payment history" screen. 2. Click on the "Physically" option. | At step 2: - The app should navigate to the screen with instructions for paying with cash. | Passed |  |  | 17/6/2025
ID-005 | Open [Payment methods] screen | Back Button Functionality | App is installed, user is logged in, and user user must have at least one unpaid booking. | Verify that the Back button works correctly | 1. Open the "Payment history" screen. 2. Click the back button (top left corner). | At step 2: - The app should return to the previous screen ("Bookings history" screen). | Passed |  |  | 17/6/2025
ID-006
ID-007
ID-008
ID-009
ID-0010
ID-0011
ID-0012
ID-0013
ID-0014
ID-0015
ID-0016
ID-0017
ID-0018
ID-0019
ID-0020
ID-0021
ID-0022
ID-0023
ID-0024

## Instruction
INSTRUCTION
This sheet is to describe/explain how to input/update in fields of the template
No. | Title | Instruction | Remarks
1 | No. | Item number | Ex: 1, 2, 3, 4
2 | PM | Project Manager
3 | BA | Business Analyst
4 | QC | Quality Control
5 | Ver. | Version number of document | Ex: 1.2, 1.3
6 | SRS/ User Stories ID | Software requirements specification/ User Stories No. Related to test cases, which just updated | Ex: User Story 321
7 | Test case ID Range | For each software requirements specification/ User Stories No., some test cases are added. List id of them on this field. | Ex: Add TC 1 ~ 14 for User Story 321, so, input "ID-001~ID-0014" in this field.
8 | Date, Creation Date | Format of Date is mm/dd/yyyy | Ex: 09/19/2017
9 | Latest Date of Test | The latest date, when finish testing. Format is mm/dd/yyyyy | Ex: Testing in a week (from 09/20/2017 to 09/26/2017), fill "09/26/2017" in this field.
10 | Platform | As an operating system, an operating environment, under which various smaller application programs/ website can be designed to run. | Ex: 1. Google Chrome Version 60.0.3112.113 on Windows 2. iPhone 5S iOS 8.4.1
11 | Main Category | A set of main parts, list main functions, which have common point, these test cases belongs. | Ex: category "Admin"
12 | Sub Category | For each Main category, set of detail parts, list detail functions, which have common point, these test cases belongs. | Ex: In category "Admin", has some sub-category: Users information, Reporter information.
13 | Pre-conditions | Any prerequisites or preconditions that must be fulfilled prior to executing the test. | Ex: Login successfully prior to Edit profile. So, in Pre-conditions field, input "Login successfully".
14 | Test Description | The summary/ objective of the test case.
15 | Steps to Perform (include Data test) | Step-by-step procedure to execute the test (include data information needed to execute the test).
16 | Expected Results | The expected result of the test.
17 | Testing result | The actual result of the test, to be filled after executing the test. Passed or Failed. Other statuses can be ‘Not Executed’ if testing is not performed and ‘Blocked’ if testing is blocked. | Ex: The actual result is same with expected result, fill "Passed".
18 | Result Recorded Date | The date of execution of the test.
19 | Who checked | The name of the person who executed the test.
20 | Remarks | Any comments on the test case or test execution.
21
22
23
24
<Add more rows if needed>